## Review Cover
Code Peer Review

Review Period
Start	2010-12-15	End	2011-02-22

Reviewer
Name:	Guillaume Olivrin
Email:	golivrin@csir.co.za
Tel:	0128413253
Department:	CSIR Meraka Institute

Developer
Name:	Willem van der Walt
Email:	wvdwalt@csir.co.za
Tel:	0128413792
Department:	CSIR Meraka Institute

Project Details
Project Number:
Project Description:	Digital Audio Editor (for the Blind)
Project Leader:	Willem van der Walt
Project Manager:
Outcomes Manager:	Nicki Koorbanally

Scope of Review
Verified that the technology package released conforms to our OSS release guidelines, / Checked source code, tested typical use cases listed in manual. / Review performed on latest files available on local repository at http://goblin.icomtek.csir.co.za/svn/dae/trunk and packaged version dae-latest.tar.bz2

Review file list
File Number	Filename		Description
1	dae.py		Main program
2	catchkey		Library
3	pickafile		Library
4	audioeditor.txt		Design Document
5	user_guide.txt		User Manual
6	README		Program Readme
7	install.sh		Program Installer
8	INSTALL		Installation Manual
9	geterm		Library
10	COPYING		License notice
11	Dae.1		Man unix entry
12	tutorial/dae_tutorial.ogg		Audio tutorial
13	tutorial/duty.wav		Example tutorial work file
14	Changelog		Changelog
15
16
17
18
19
20

## Issue Log
Number	Filename	Code Line	Issue Description	Issue identification
1	dae.py		Fix rewinding
2	dae.py, catchkey, pickafile	0	Add License header to each files (GNU General Public License v2 +) and Author
3	dae, dae.py	1	for less confusion between Python and Perl DAE, mv dae dae.perl or dae.pl
4	dae.py	1	problem when using python2.5 (no longer packaged) not finding pyeca. Solved forcing python2.6. Fix the dae script to invoke python, not python2.5
5	dae.py, user_guide.txt		problem using dae under a graphical console command prompt. The function keys F1 etc are not caught, all receive 0 or start another app. Add this to documentation, that DAE must be run from a non-graphical shell terminal environment. (e.g. ctrl-alt-2) Detect when in non console mode and warn?
6	pickafile	52	getterm: command not found
7			mp3 not fully supported
8			ogg not fully supported
9	dae.py, catchkey, pickafile		Install script to check/get library dependencies, run as sudo to copy dae.py to /usr/bin/dae, catchkey to /usr/bin/catchkey, pickafile to /usr/bin/pickafile
10	user_guide.txt		INSTALLATION
11	lib		Upon quitting / recording / inserting file: / Exception attribute error: “'non type' object as no attribute 'maxint'” in <Bounded method Popen3.__delete__ of popen2.Popen3 instance ...
12		579, module user_control(), / 525 record_realtime() / 326 insert_file(“realtime.wav”, mainpos ), / 461 in insert_file os.unlink(infile)	Problem during recording / OSError : no such file or directory “guirecords.wav” / Does the file needs to be created before recording? Yes, touch guidrecords.wav seems to solve it
	dae.py		playback doesn't seem to work reliably. When pressing F1 to play and then checking the progression of the playback using the w key, it seems that the playback literally jumps from 0 to the end of file position.

## Action Log
Number	Filename	Code Line	Issue Description	Resolution Comment	Resolution Status	Resolution close date
1	dae.py		Fix rewinding	Fixed	Resolved	2011-01-18
2	dae.py, catchkey, pickafile	0	Add License header to each files (GNU General Public License v2 +) and Author	COPYING	Resolved	2011-02-17
3	dae, dae.py	1	for less confusion between Python and Perl DAE, mv dae dae.perl or dae.pl	Perl code moved to separate directory and excluded from deliverable.	Resolved	2011-02-17
4	dae.py	1	problem when using python2.5 (no longer packaged) not finding pyeca. Solved forcing python2.6. Fix the dae script to invoke python, not python2.5	Now use #!/usr/bin/python but pyeca still create depreciation problems when using python2.6 (entered as a new/separate issue and action)	Resolved	2011-02-17
5	dae.py, user_guide.txt		problem using dae under a graphical console command prompt. The function keys F1 etc are not caught, all receive 0 or start another app. Add this to documentation, that DAE must be run from a non-graphical shell terminal environment. (e.g. ctrl-alt-2) Detect when in non console mode and warn?	added special mention to user_guide.txt	Resolved	2011-01-19
6	pickafile	52	getterm: command not found	install.sh script	Resolved	2011-02-17
7			mp3 not fully supported	in user_guide.txt	Answered
8			ogg not fully supported	in user_guide.txt	Answered
9	dae.py, catchkey, pickafile		Install script to check/get library dependencies, run as sudo to copy dae.py to /usr/bin/dae, catchkey to /usr/bin/catchkey, pickafile to /usr/bin/pickafile	install.sh script + INSTALL manual	Resolved	2011-02-17
10	user_guide.txt		INSTALLATION	install.sh script + INSTALL manual	Resolved	2011-02-17
11	lib		Upon quitting / recording / inserting file: / Exception attribute error: “'non type' object as no attribute 'maxint'” in <Bounded method Popen3.__delete__ of popen2.Popen3 instance ...	This problem probably caused by library pyeca legacy compatibility with Python1.6. Should prescribe using with Python 1.5 for this release of DAE.	Pending
12		579, module user_control(), / 525 record_realtime() / 326 insert_file(“realtime.wav”, mainpos ), / 461 in insert_file os.unlink(infile)	Problem during recording / OSError : no such file or directory “guirecords.wav” / Does the file needs to be created before recording? Yes, touch guidrecords.wav seems to solve it	Now create a 1s empty wav file with headers	Resolved	2011-02-17
	dae.py		playback doesn't seem to work reliably. When pressing F1 to play and then checking the progression of the playback using the w key, it seems that the playback literally jumps from 0 to the end of file position.		Resolved	2011-02-17

## Approval
Approval

Reviewer
Name:	Guillaume Olivrin
Date:	2011/02/22
Declaration:	I declare that the submitted files have been reviewed and all identified issues have now been resolved
Signature:

Developer
Name:	Willem van der Walt
Date:
Declaration:	I declare that the identified issues from the reviewer have been completely resolved with no further outstanding issues
Signature:

Project Manager
Name:
Date:
Declaration:	I declare that the submitted files are suitable for inclusion on the software repository and added to the ToDB database
Signature:

Outcomes Manager
Name:	Nicki Koorbanally
Date:
Declaration:	I declare that the submitted files are suitable for inclusion on the software repository and added to the ToDB database
Signature: